## REPORT
Test ID | Name | To Be Executed | Passed | Blocked | Total Scenario | Total Bug | Persentase
T01.01 | Landing page | 1 | 15 | 3 | 23 | 5 | 95.65%
T01.02 | Listing Property | 11 | 0 | 11 | 11 | 0 | 0%
T01.03 | FAQ | 0 | 6 | 0 | 6 | 0 | 100%
T01.04 | Kerja Sama | 0 | 2 | 0 | 2 | 0 | 100%
T02.01 | Floating Whatsapp | 0 | 1 | 0 | 1 | 0 | 100%
T02.02 | Why Kostzy | 0 | 1 | 0 | 1 | 0 | 100%
T02.03 | Tentang Kostzy | 0 | 1 | 0 | 1 | 0 | 100%
T02.04 | News | 0 | 1 | 0 | 1 | 0 | 100%
Total |  | 12 | 27 | 14 | 46 | 5 | 21.74%

## Landing Page
Summary
| SCENARIO PROGRESS |  | TOTAL PERCENT |  |  |  |  | Failed | To Be Executed
| # Test Scenario : | 23 | [5 empty] | Passed | Completed
| # Completed : | 22 | % Completed : | 95.65% |  |  |  | Blocked | Change Request
| # Passed : | 15 | % Passed : | 65.22% |  |  |  |  | After Go Live
| # Failed : | 5 | % Failed : | 21.74% |  |  |  |  | Dropped
| # To Be Executed : | 1 | % To Be Executed : | 4.348%
| # Blocked : | 3 | % Blocked : | 300%
| # Non Blocked : | -2 | % Non Blocked : | -200%
| # ChangeRequest : | 0 | % ChangeRequest : | 0%
Test ID | Name | Test Description | Data | Expected Result | Actual Result | Condition | Status | Test Date | Remark | Scenario By | Tested By
T01.01 | Web Public - Landing Page
UI Case - Header
T01.01.01 | Cek logo Koszty | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek logo |  | Dapat dilakukan |  | Completed | Passed | 2023-07-15
T01.01.02 | Cek menu navigasi - Cari kost | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Klik Cari kos |  | Dapat dilakukan |  | Completed | Passed | 2023-07-15
T01.01.03 | Cek menu navigasi - Tentang Kostzy | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek logo |  | Dapat dilakukan Menampilkan halaman tentang kostzy |  | Completed | Passed | 2023-07-15
T01.01.04 | Cek menu navigasi - Why Kostzy | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek logo |  | Dapat dilakukan Menampilkan halaman why kostzy |  | Completed | Passed | 2023-07-15
UI Case - Cari Kost
T01.01.04 | Cek dropdown Filter lokasi | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek filter |  | Dapat dilakukan Menampilkan dropdown data lokasi |  | Completed | Passed | 2023-07-15
T01.01.05 | Cek dropdown filter fasilitas | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek filter |  | Dapat dilakukan Menampilkan dropdown data fasilitas |  | Completed | Passed | 2023-07-15
T01.01.06 | Cek filter Range harga | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek filter |  | Dapat dilakukan |  | Completed | Passed | 2023-07-15
T01.01.07 | Cek button Cari sekarang | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Klik button cari Sekarang |  | Dapat dilakukan |  | Completed | Failed | 2023-07-15 | Unhandled Runtime Error TypeError: Cannot read properties of null (reading 'lat')
UI Case - Slider Image
T01.01.08 | Cek Slider | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Klik button cari Sekarang |  | Dapat dilakukan |  | Completed | Passed | 2023-07-15
UI - Background Image
T01.01.09 | Cek backgroud | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek background |  | Dapat dilakukan |  | Completed | Failed | 2023-07-15 | Ada sedikit bagian kurang rapi di section Temukan hunian Kota Populer (Landing Page)
UI Case - Recomended Property
T01.01.10 | Cek Recomended Property | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek recomended property |  | Dapat dilakukan Menampilkan Recomended Property : - Gambar - Kota - Nama Property - Rent Price |  | Completed | Failed | 2023-07-15 | Property ny tidak bisa di klik Tidak bisa menampilkan detail property
UI Case - Popular City
T01.01.11 | Cek popular city | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek popular citu |  | Dapat dilakukan Menampilkan list card berupa : - Gambar kota - kota |  | Completed | Failed | 2023-07-15 | Unhandled Runtime Error TypeError: Cannot read properties of undefined (reading 'map')
UI Case - Testimonial
T01.01.12 | Cek Testimonial | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek testimonial |  | Dapat dilakukan Menampilkan list berupa : - Name - Testimonial - Property name |  | Completed | Failed | 2023-07-15 | Konten tidak muncul
T01.01.13 | Cek Arrow button | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek testimonial 3. Klik button Arrow |  | Dapat dilakukan |  | To Be Executed | Blocked | 2023-07-15
UI Case - Galery Aktifitas Kostzy
T01.01.14 | Cek galeri aktifitas | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek galery aktifitas |  | Dapat dilakukan Menampilkan gambar branding Kostzy |  | Completed | Blocked | 2023-07-15 | Gambar tidak muncul
T01.01.15 | Cek button Lihat Lebih Banyak | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek galery aktifitas 3. Klik button Selengkapnya |  | Dapat dilakukan Menampilkan halaman galeri aktivitas kostzy berupa : - penjelasan halaman galeri aktivitas kostzy - Gambar&video aktivitas kostzy |  | Completed | Blocked | 2023-07-15
UI Case - Download Apps
T01.01.16 | Cek Section Download Apps | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek Section download apps |  | Dapat dilakukan Menampilkan : - penjelasan download - image handphone - download on app store. berisi link yang jika di klik akan menuju halaman download Kostzy di App store. - download on google play. berisi link yang jika di klik akan menuju halaman download Kostzy di Play store. - QR Code. berisi link yang jika di scan akan menuju halaman download Kostzy di Play store. |  | Completed | Passed | 2023-07-15
T01.01.17 | Cek Download by App store | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek galery aktifitas 3. Klik button Selengkapnya |  | Dapat dilakukan Redirect ke halaman appstore |  | Completed | Passed | 2023-07-15 | Tapi belum redirect ke app store
T01.01.18 | Cek donwload by google play | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek galery aktifitas 3. Klik button Selengkapnya |  | Dapat dilakukan Redirect ke halaman playstore |  | Completed | Passed | 2023-07-15 | Tapi belum redirect ke google store
UI Case News
T01.01.19 | Cek Section News | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek Section News |  | Dapat dilakukan Menampilkan : - image - posting date - Title - News category |  | Completed | Passed | 2023-07-15
T01.01.20 | Cek detail news | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek Section News 3. Klik salah satu News |  | Dapat dilakukan Menampikan detail News |  | Completed | Passed | 2023-07-15
T01.01.21 | Cek button Selengkapnya | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek Section News 3. Klik button selengkapny |  | Dapat dialkukan Redirect ke halaman detail berita |  | Completed | Passed | 2023-07-15
UI Case - Footer
T01.01.22 | Cek list footer | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Cek Footer |  | Dapat dilakukan Menampilkan : - Logo Kostzy - Alamat lengkap Head Office Kostzy - No Telp/WA utama kostzy - email sales Kostzy - Discover why kostzy →jika di klik maka menuju halaman Why Kostzy FAQ→ jika di klik maka menuju halaman FAQ - Company News→ jika di klik redirect ke halaman “News” Partnership → jika di klik redirect ke halaman “Brand Partnership” Mitra Properti Owner → jika di klik redirect ke halaman “Mitra Property” Tentang Kostzy → jika di klik redirect ke halaman “Tentang Kostzy” - Social Media instagram : @thekostzy facebook : The Kostzy twitter : @thekostzy youtube : @thekostzy224 tiktok : @thekostzy jika di klik maka menuju ke profil masing masing social media - Download App (download on app store, download on playstore, dan qr code Image yang berisi link download on playstore kostzy) - Privacy Policy→ jika di klik maka menuju halaman Privacy Policy. text pada halaman ini diisi menggunakan hardcode Term & Condition → jika di klik maka menuju halaman Term & Condition Copyright |  | Completed | Passed | 2023-07-15

## Listing Property
Summary
| SCENARIO PROGRESS |  | TOTAL PERCENT |  |  |  |  | Failed | To Be Executed
| # Test Scenario : | 11 | [5 empty] | Passed | Completed
| # Completed : | 0 | % Completed : | 0% |  |  |  | Blocked | Change Request
| # Passed : | 0 | % Passed : | 0% |  |  |  |  | After Go Live
| # Failed : | 0 | % Failed : | 0% |  |  |  |  | Dropped
| # To Be Executed : | 11 | % To Be Executed : | 100%
| # Blocked : | 11 | % Blocked : | 100%
| # Non Blocked : | 0 | % Non Blocked : | 0%
| # ChangeRequest : | 0 | % ChangeRequest : | 0%
Test ID | Name | Test Description | Data | Expected Result | Actual Result | Condition | Status | Test Date | Remark | Scenario By | Tested By
T01.02 | Web Publik - Listing Property
UI Case
T01.02.01 | Cek halaman Detail Properti | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Klik properti 3. Cek detail properti |  | Dapat dilakukan Menampilkan data detail property : - Gambar Kos Nama Kos area(Format: kota + area) Alamat lengkap Kos status deskripsi (bersifat umum dan lebih menjelaskan mengenai kos) deskripsi lokasi (menjelaskan posisi kos dalam lokasi tersebut. bisa terkait lokasi yang strategis dsb) Fasilitas kamar(Ikon & deskripsi fasilitas) Fasilitas umum(Ikon & deskripsi fasilitas) layanan(Ikon & deskripsi layanan) transportasi umum(Ikon & deskripsi transportasi umum) tempat terdekat(Ikon & deskripsi tempat terdekat) - Tab menu Kamar Gambar kamar Tipe kamar Label berapa kamar yang tersedia Tipe hunian → campur/pria/wanita Luas kamar (ex: 2 meter persegi) Luas tempat tidur (ex: 160x100) Detail fasilitas kamar deskripsi kamar Harga fix per tipe kamar Jika penuh : Tombol “Join Waiting List” dan Tombol “Chat kami” Jika belum penuh : Tombol “Fix Booking”, Tombol “Request Survey” dan Tombol “Chat kami” - Tab Lokasi Map lokasi |  | To Be Executed | Blocked | 2023-07-15 | Gabisa diklik
T01.02.02 | Cek button pesan kost | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Klik properti 3. Klik button Pesan kost |  | Dapat dilakukan |  | To Be Executed | Blocked | 2023-07-15
T01.02.03 | Cek button Survey | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Klik properti 3. Klik button Survey |  | Dapat dilakukan |  | To Be Executed | Blocked | 2023-07-15
T01.02.04 | Cek button Chat kami | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Klik properti 3. Klik button Chat kami |  | Dapat dilakukan |  | To Be Executed | Blocked | 2023-07-15
Use Case
T01.02.05 | User dapat search property | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Klik properti 3. Klik Cari kos 4. Input fiter Lokasi 5. Input filter fasilitas 6. Input Range harga 7 Klik button Cari Sekarang |  | Dapat dilakukan Sistem menampilkan hasil pencarian data berupa list, dengan detail berikut: - Gambar Kos (1 gambar) - Nama Kos - Area(Format: area + kota) - Status → ex: 5 kamar tersedia / penuh -near_transport → ex: 7 menit dari halte sunter mall - near_place → ex: 10 menit dari PIK Avenue - Harga Asli start from Rp xx - Harga Diskon → jika di setting di Backoffice - Tipe hunian → Campur, pria,wanita sistem juga menampilkan hasil hasil pencarian data berupa maps pointing dengan detail berikut: - Gambar Kos (1 gambar) - Nama Kos - Harga Asli start from Rp xx - Harga Diskon |  | To Be Executed | Blocked | 2023-07-15
T01.02.06 | User dapat lihat detail Properti | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Klik properti 3. Cek detail properti |  | Dapat dilakukan |  | To Be Executed | Blocked | 2023-07-15
T01.02.07 | User dapat Create Survey | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Klik properti 3. Cek detail properti 4. Klik button Survey |  | Dapat dilakukan |  | To Be Executed | Blocked | 2023-07-15
T01.02.08 | User input semua mandatory field pada form Survey dengan data valid | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Klik properti 3. Cek detail properti 4. Klik button Survey 5. Input data 6. Klik button Schedule event |  | Berhasil Create Survey |  | To Be Executed | Blocked | 2023-07-15
T01.02.09 | User input beberpa mandatory field pada form Survey dengan data valid | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Klik properti 3. Cek detail properti 4. Klik button Survey 5. Input data 6. Klik button Schedule event |  | Gagal create survey Menampilkan alert message pada mandatory field yang kosong - field input name "Please Input yourname" - Field input detail "Pleas input a valid email address" - Filed input number "Please input a valid phone number" |  | To Be Executed | Blocked | 2023-07-15
T01.02.10 | User mengkosongkan semua mandatory field pada form Survey | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Klik properti 3. Cek detail properti 4. Klik button Survey 5. Klik button Schedule event |  | Gagal create Survey Menampilkan alert message pada semua mandatory field yang kosong : - field input name "Please Input yourname" - Field input detail "Pleas input a valid email address" - Filed input number "Please input a valid phone number" |  | To Be Executed | Blocked | 2023-07-15
T01.02.11 | User dapat mengirimkan pertanyaan terkait property yang sedang dilihat ke Kostzy melalui WA | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Klik properti 3. Cek detail properti 4. Klik button Survey 5. Klik button Chat kamit |  | Dapat dilakukan Redirect ke halaman Whatsapp |  | To Be Executed | Blocked | 2023-07-15

## FAQ
Summary
| SCENARIO PROGRESS |  | TOTAL PERCENT |  |  |  |  | Failed | To Be Executed
| # Test Scenario : | 6 | [5 empty] | Passed | Completed
| # Completed : | 6 | % Completed : | 100% |  |  |  | Blocked | Change Request
| # Passed : | 6 | % Passed : | 100% |  |  |  |  | After Go Live
| # Failed : | 0 | % Failed : | 0% |  |  |  |  | Dropped
| # To Be Executed : | 0 | % To Be Executed : | 0%
| # Blocked : | 0 | % Blocked : | #DIV/0!
| # Non Blocked : | 0 | % Non Blocked : | #DIV/0!
| # ChangeRequest : | 0 | % ChangeRequest : | 0%
Test ID | Name | Test Description | Data | Expected Result | Actual Result | Condition | Status | Test Date | Remark | Scenario By | Tested By
T01.03 | Web Public - FAQ
UI Case
T01.03.01 | Cek halaman Faq | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Footer 3. Klik FAQ |  | Dapat dilakukan Menampilkan halaman FAQ |  | Completed | Passed | 2023-07-15
T01.03.02 | Cek button Search | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Footer 3. Klik FAQ 4. Klik button Search |  | Dapat dilakukan |  | Completed | Passed | 2023-07-15
T01.03.03 | Cek field search | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Footer 3. Klik FAQ 4. Input field Search |  | Dapat dilakukan |  | Completed | Passed | 2023-07-15
T01.03.04 | Cek dropdown list data topik yg sering dicari | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Footer 3. Klik FAQ |  | Dapat dilakukan Menampilkan dropdown jawaban |  | Completed | Passed | 2023-07-15
Use Case
T01.03.05 | User dapat melihat jawaban dari pertanyaan yang sering di tanyakan a di menu FAQ di Kostzy melalui Web Public berdasarkan kategori FAQ | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Footer 3. Klik FAQ |  | Dapat dilakukan Menampilkan list pertanyaan berdasrkan kategory FAQ |  | Completed | Passed | 2023-07-15
T01.03.06 | User dapat mencari jawaban dengan cara search maupun klik salah satu accordion terkait pertanyaan yang sesuai | Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Footer 3. Klik FAQ 4. Input field search 5. Klik button search |  | Dapat dilakuan Menampilkan list accordion berdasarkan search |  | Completed | Passed | 2023-07-15

## Kerja Sama
Summary
| SCENARIO PROGRESS |  | TOTAL PERCENT |  |  |  |  | Failed | To Be Executed
| # Test Scenario : | 2 | [5 empty] | Passed | Completed
| # Completed : | 2 | % Completed : | 100% |  |  |  | Blocked | Change Request
| # Passed : | 2 | % Passed : | 100% |  |  |  |  | After Go Live
| # Failed : | 0 | % Failed : | 0% |  |  |  |  | Dropped
| # To Be Executed : | 0 | % To Be Executed : | 0%
| # Blocked : | 0 | % Blocked : | #DIV/0!
| # Non Blocked : | 0 | % Non Blocked : | #DIV/0!
| # ChangeRequest : | 0 | % ChangeRequest : | 0%
Test ID | Name | Test Description | Data | Expected Result | Actual Result | Condition | Status | Test Date | Remark | Scenario By | Tested By
T01.04 | Web Public - Kerja Sama
UI Case
T01.04.01 | Cek halaman Kerja Sama | "Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Footer 3. Company 4. Kerjasama |  | Menampilkan halam kerjasama dengan detail : - Kerja sama antar brand - Hubungi kami (Email, Whatsapp) - Brand bekerja sama dengan kostzy (image) |  | Completed | Passed | 2023-07-15
T01.04.02 | Cek halaman Mitra Property | "Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Footer 3. Company 4. Mitra Property |  | Menampilkan halaman Brand Partnership dengan detail berikut: - Bermitra Dengan Kostzy - Hubungi kami (Email, Whatsapp) - We Understand Your Problem - Why kostzy - what we do - Benefit (tabel) - Brand Partnership (image) - mitra property (image) - news (News category, Title,image,posting date) |  | Completed | Passed | 2023-07-15

## Floating Whatsapp
Summary
| SCENARIO PROGRESS |  | TOTAL PERCENT |  |  |  |  | Failed | To Be Executed
| # Test Scenario : | 1 | [5 empty] | Passed | Completed
| # Completed : | 1 | % Completed : | 100% |  |  |  | Blocked | Change Request
| # Passed : | 1 | % Passed : | 100% |  |  |  |  | After Go Live
| # Failed : | 0 | % Failed : | 0% |  |  |  |  | Dropped
| # To Be Executed : | 0 | % To Be Executed : | 0%
| # Blocked : | 0 | % Blocked : | #DIV/0!
| # Non Blocked : | 0 | % Non Blocked : | #DIV/0!
| # ChangeRequest : | 0 | % ChangeRequest : | 0%
Test ID | Name | Test Description | Data | Expected Result | Actual Result | Condition | Status | Test Date | Remark | Scenario By | Tested By
T01.05 | Web Public - Floating Whatsapp
UI Case
T01.05.01 | Cek Floating Whatsapp | """Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Klik Floating App |  | Dapat dilakukan Redirect ke whatsapp Muncul disemua page |  | Completed | Passed | 2023-07-15 | Ketutup di layar laptop resolusi 14 ins

## Why Kostzy
Summary
| SCENARIO PROGRESS |  | TOTAL PERCENT |  |  |  |  | Failed | To Be Executed
| # Test Scenario : | 1 | [5 empty] | Passed | Completed
| # Completed : | 1 | % Completed : | 100% |  |  |  | Blocked | Change Request
| # Passed : | 1 | % Passed : | 100% |  |  |  |  | After Go Live
| # Failed : | 0 | % Failed : | 0% |  |  |  |  | Dropped
| # To Be Executed : | 0 | % To Be Executed : | 0%
| # Blocked : | 0 | % Blocked : | #DIV/0!
| # Non Blocked : | 0 | % Non Blocked : | #DIV/0!
| # ChangeRequest : | 0 | % ChangeRequest : | 0%
Test ID | Name | Test Description | Data | Expected Result | Actual Result | Condition | Status | Test Date | Remark | Scenario By | Tested By
T01.06 | Web Public - Why Kostzy
UI Case
T01.06.01 | Cek halaman Why Kostzy | "Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Header 2. Klik Why Kostzy |  | Menampilkan halaman Brand Partnership dengan detail berikut: - penjelasan Why Kostzy - Langkah - langkah mencari kost di Kostzy - kumpul bersama Kozmate (image) - perbandingan menggunakan Kostzy dan yang lain - testimoni (carousel) |  | Completed | Passed | 2023-07-15

## Tentang Kostzy
Summary
| SCENARIO PROGRESS |  | TOTAL PERCENT |  |  |  |  | Failed | To Be Executed
| # Test Scenario : | 1 | [5 empty] | Passed | Completed
| # Completed : | 1 | % Completed : | 100% |  |  |  | Blocked | Change Request
| # Passed : | 1 | % Passed : | 100% |  |  |  |  | After Go Live
| # Failed : | 0 | % Failed : | 0% |  |  |  |  | Dropped
| # To Be Executed : | 0 | % To Be Executed : | 0%
| # Blocked : | 0 | % Blocked : | #DIV/0!
| # Non Blocked : | 0 | % Non Blocked : | #DIV/0!
| # ChangeRequest : | 0 | % ChangeRequest : | 0%
Test ID | Name | Test Description | Data | Expected Result | Actual Result | Condition | Status | Test Date | Remark | Scenario By | Tested By
T01.07 | Web Public - Tentang Kostzy
T01.07.01 | Cek halaman Why Kostzy | "Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Header 2. Klik Why Kostzy |  | Menampilkan halaman Brand Partnership dengan detail berikut: - Penjelasan halaman news - berita terbaru (News category, Title,image,posting date) - Brand Partnership (image) - mitra property (image) |  | Completed | Passed | 2023-07-15

## News
Summary
| SCENARIO PROGRESS |  | TOTAL PERCENT |  |  |  |  | Failed | To Be Executed
| # Test Scenario : | 1 | [5 empty] | Passed | Completed
| # Completed : | 1 | % Completed : | 100% |  |  |  | Blocked | Change Request
| # Passed : | 1 | % Passed : | 100% |  |  |  |  | After Go Live
| # Failed : | 0 | % Failed : | 0% |  |  |  |  | Dropped
| # To Be Executed : | 0 | % To Be Executed : | 0%
| # Blocked : | 0 | % Blocked : | #DIV/0!
| # Non Blocked : | 0 | % Non Blocked : | #DIV/0!
| # ChangeRequest : | 0 | % ChangeRequest : | 0%
Test ID | Name | Test Description | Data | Expected Result | Actual Result | Condition | Status | Test Date | Remark | Scenario By | Tested By
Web Public - News
T01.08 | UI Case
T01.08.01 | Cek halaman Berita | "Precondition : Browser : https://kostzy.festiware.com/ Start : 1. Home 2. Footer 3. Berita |  | Menampilkan halaman Brand Partnership dengan detail berikut: - Penjelasan halaman news - berita terbaru (News category, Title,image,posting date) - Brand Partnership (image) - mitra property (image) |  | Completed | Passed | 2023-07-15